## Sprint Plan
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
| week6 | Create User Story and Sprint Plan
|  | Complete sprint plan | Team | Complete | Low
|  | Complete user story | Team | Complete | Low
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
| week7 | UI Design
|  | Complete all designs | Team | Complete | Low
|  | Review user story | Frontend | Complete | Low
|  | Review sprint plan | Frontend | Complete | Low
|  | Setup project management tool | Frontend | Complete | Low
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
| week8 | Release Plan for Version 1.0: Must-Have Features
|  | Implement user account creation and login system for multi-device access. | Backend | Complete | High
|  | Develop functionality to allow users to create, save, and manage daily workout plans. | Team | In Progress | Medium
|  | Enable users to add new exercises to their workout plans and remove unwanted ones. | Team | In Progress | Medium
|  | Implement body part selection for targeted workout creation. | Team | In Progress | Medium
|  | Create an overview page displaying planned workouts, exercises, and completion status. | Team | In Progress | Medium
|  | Build a feature to track past workouts and visualize user progress over time. | Backend | Complete | High
|  | Design a simple, intuitive user interface for easy navigation and interaction. | Backend | Complete | High
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
| week9 | Assessment 1: Project Progress and Performance
|  | Poject walkthrough video | Frontend | In Progress | Medium
|  | Functional Prototype | Backend | In Progress | Medium
|  | Test-Driven Development | Backend | In Progress | Medium
|  | Version Control Workflow | Team | In Progress | Medium
|  |  |  | In Progress | Medium
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
| week 10 | Release Plan for Version 1.1: Should-Have Features
Implement a reminder feature to notify users about upcoming workouts.
Add a timer feature to track rest periods between exercises.
Develop a timer to track the overall duration of a workout session.
Allow users to save their workout plans as reusable templates for future use.
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
| week 11 | Continuous Integration
Enhanced Prototype
Build Script
Automated Build Server
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
| week 12 | Release Plan for Version 2.0: Could-Have Features
Implement a goal-setting feature for users to track their personal fitness milestones.
Enable users to share workout progress and achievements with friends or coaches.
Add functionality to track and display health metrics like weight, BMI, and body fat percentage.
Ensure seamless login and data synchronization across multiple devices for user accounts.
At Risk? | Date | Task Description | RESPONSIBLE | STATUS | PRIORITY | COMMENTS
week 13

## Users Story
1 | Simple UI Design | Easy-to-Learn Interface for New Users | User | Have an app interface to be simple and easy to understand | I can quickly learn how to use the app. | I am using the app for the first time. | I open the app and start exploring its features. | the app should provide a clean, user-friendly interface that guides me through the features. | 3 | Must have
2 | Simple UI Design | Large, Clear Buttons for Older Users | User | Have buttons and text that are large and clear | I can easily navigate the app. | I have difficulty seeing small text or buttons. | I interact with the app. | the app should display large and clearly marked buttons for easy access. | 2 | Must have
3 | Simple UI Design | Clean Layout for First-Time Users | User | Have a clean and uncluttered layout | I am not overwhelmed by too many options. | I have just downloaded the app. | I open it for the first time. | the interface should present a minimal, clutter-free layout. | 3 | Must have
4 | Simple UI Design | Workout Routine Timer | Fitness User | Have a timer for my overall session | I can manage my time efficiently, ensuring I complete my workout within a specific timeframe | I have initialised my workout routine for the day | I set a timer for the duration of my workout | the app should start counting | 2 | Could have
5 | Simple UI Design | Account | Personal Trainer | Login to my trainees account | I can track their workout logs. | A personal trainer wants to track their trainees progress | They log in to a trainees' account | They should be able to view and track their trainees' workout logs | 2 | Must have
6 | Simple UI Design | Have an Account | User | Have an account | I have private worklogs I can access from multiple different devices. | A user wants to access their workout logs from different devices | They create and log in to their account | They should have private workout logs accessible from multiple devices. | 2 | Must have
7 | Daily Workout Creation | Create Daily Workout Plan for Fitness Enthusiasts | Fitness user | Create daily workout plans | I can stay on track with my fitness goals. | I want to track my fitness progress. | I create a new workout plan. | the app should allow me to easily set up a routine for the day. | 3 | Must have
8 | Daily Workout Creation | Quick Workout Plan for Beginners | Fitness user | Quickly create a daily workout plan | I can track my progress easily. | I am new to fitness and the app. | I want to create a simple workout plan. | the app should guide me through creating a beginner-level workout plan. |  | Must have
9 | Daily Workout Creation | Create an excersise | User | Create an excercise | I can add it to the logger for future use. | The user wants to add a new exercise to their workout plan | The user accesses the "Create an exercise" feature | They should able to create a new exercise and add it to the list for future workouts. | 2 | Must have
10 | Daily Workout Creation | Delete an excercise | User | Delete an excercise | I can delete an excercise If I believe I have no plans to do it due to injury concerns. | The user wants to remove an exercise they no longer plan to use | The user accesses the "Delete an exercise" feature | They should be able to remove the exercise from their list if they have no plans to do it. | 2 | Must have
11 | Daily Workout Creation | Schedule Future Workouts | User | Schedule my future workout plans | I can have a structured fitness routine ahead of time. | I want to plan my workouts in advance. | I access the workout scheduling feature. | the app should let me schedule future workouts for the upcoming days. | 2 | Could have
12 | Daily Workout Creation | Auto-Generated Daily Workout Suggestions | User | The app to generate daily workout suggestions based on time or goals | I can exercise more efficiently. | I am unsure what exercises to perform today. | I want the app to suggest a workout. | the app should generate a routine based on my fitness goals and time available. | 3 | Could have
13 | Daily Workout Creation | Video Tutorial | User | See how to perform the excercise | I can do it with proper form. |  | They access the exercise and "Video Guide" feature | They should able to see a video guide that demonstrates the correct form of the exercise. | 3 | Wont have
14 | Body Part Selection for Workouts | Targeted Body Part Workouts | User | Select specific body parts for my workout | I can target those areas. | I want to work on a specific part of my body. | I start creating my workout. | the app should allow me to choose body parts and display relevant exercises. | 2 | Should have
15 | Body Part Selection for Workouts | Quick Body Part Workout Search | User | Quickly find exercises by body part | I save time in selecting the right workout. | I have limited time for my workout. | I need to find exercises quickly. | the app should display a list of exercises based on body parts to speed up the selection process. | 2 | Should have
16 | Body Part Selection for Workouts | Personalized Workouts for Different Muscle Groups | User | Personalized workout suggestions for different muscle groups | I can balance my training. | I want to focus on balancing my muscle training. | I set up my workout plan. | he app should suggest exercises for different muscle groups. | 2 | Could have
17 | Body Part Selection for Workouts | Exclude Body Parts in Workouts for Injury Prevention | User | Exclude certain body parts from the workout | I don’t aggravate my injury. | I am recovering from an injury. | I create a workout. | the app should allow me to exclude exercises that involve the injured body part. | 2 | Wont have
18 | Workout Overview | Daily Workout Overview | Fitness user | See an overview of all planned workouts for the day | I know what exercises I need to complete. | I have created a workout plan for today. | I open the app. | the app should display an overview of all exercises planned for the day. | 2 | Must have
19 | Workout Overview | Workout History and Progress Review | Fitness user | See a history of past workouts | I can analyze my progress. | that I want to review my past workouts. | I select the history tab. | the app should show my workout history and progress. | 3 | Must have
20 | Workout Overview | Share Workout Overview with Coach or Friends | Fitness user | Share my workout overview with my coach or friends | I can get feedback or encouragement. | I want to share my workout progress. | I select the share option. | the app should allow me to send my workout overview to a coach or friends. | 3 | Should have
21 | Workout Overview | Overview of Completed and Upcoming Workouts | Fitness user | See both completed and upcoming workouts in one place | I can better organize my fitness routine. | I want to compare my current performance with past sessions. | I open the performance comparison section. | the app should show my improvements or declines. | 3 | Must have
22 | Comprehensive Workout & Health Management | Track Metrics | Fitness user | Track various health and fitness metrics (such as body weight, body fat %, sleep) | I can monitor my progress and make decisions based on those parameters. | The user wants to monitor their fitness progress | The user accesses the "Track Metrics" feature | They should be able to input, view and update their health and fitness metrics such as height, weight, bmi, body fat percentage, blood pressure and sleep. | 3 | Could have
23 | n/a
24 | Comprehensive Workout & Health Management | Track Water Intake | Fitness user | Log and monitor my daily water intake | I can stay hydrated and maintain healthy hydration habits | I am using the app throughout the day | I input the amount of water I drink | The app should track and display my total water intake for the day | 4 | Should have
25 | n/a
26 | Comprehensive Workout & Health Management | Sync with Fitness Tracker Devices | Fitness user | Sync the app with my fitness tracker or smartwatch | I can automatically import my heart rate, steps, and other health data | I have connected my device to the app | I complete a workout | The app should sync the workout and health data from my fitness tracker device | 3 | Could have
27 | Comprehensive Workout & Health Management | Adjust Workout Difficulty | Fitness user | Modify the intensity of my workout routine based on my fitness level | I can progress gradually without overexerting myself | I am viewing a workout routine | I press the “Adjust Difficulty” button | The app should allow me to change the number of reps, sets, or resistance level | 2 | Could have
28 | Simple UI Design | Tutorial | User | I want to be guided step by step on what to do | I can navigate through the app without frustrations | I am in the app | I am accessing its features | The app should teach me how to use it |  | Wont have
Story ID | Feauture Functionality | Story Title | As a | I want to | so that | given… | when.. | then.. | Story Point | Priority

## New User Story (latest)
1 | Simple UI Design | Easy-to-Learn Interface for New Users | User | Have an app interface to be simple and easy to understand | I can quickly learn how to use the app. | 3 | Must have
2 | Simple UI Design | Large, Clear Buttons for Older Users | User | Have buttons and text that are large and clear | I can easily navigate the app. | 2 | Should have
3 | Simple UI Design | Clean Layout for First-Time Users | User | Have a clean and uncluttered layout | I am not overwhelmed by too many options. | 3 | Must have
4 | Simple UI Design | Workout Routine Timer | Fitness User | Have a timer for my overall session | I can manage my time efficiently, ensuring I complete my workout within a specific timeframe | 2 | Could have
5 | Simple UI Design | Account | Personal Trainer | Login to my trainees account | I can track their workout logs. | 2 | Must have
6 | Simple UI Design | Have an Account | User | Have an account | I have private worklogs I can access from multiple different devices. | 2 | Must have
7 | Daily Workout Creation | Create Daily Workout Plan for Fitness Enthusiasts | Fitness user | Create daily workout plans | I can stay on track with my fitness goals. | 3 | Should have
8 | Daily Workout Creation | Quick Workout Plan for Beginners | Fitness user | Quickly create a daily workout plan | I can track my progress easily. |  | Should have
9 | Daily Workout Creation | Create an excersise | User | Create an excercise | I can add it to the logger for future use. | 2 | Must have
10 | Daily Workout Creation | Delete an excercise | User | Delete an excercise | I can delete an excercise If I believe I have no plans to do it due to injury concerns. | 2 | Must have
11 | Daily Workout Creation | Schedule Future Workouts | User | Schedule my future workout plans | I can have a structured fitness routine ahead of time. | 2 | Should have
12 | Daily Workout Creation | Auto-Generated Daily Workout Suggestions | User | The app to generate daily workout suggestions based on time or goals | I can exercise more efficiently. | 3 | Should have
13 | Daily Workout Creation | Video Tutorial | User | See how to perform the excercise | I can do it with proper form. | 3 | Should have
14 | Body Part Selection for Workouts | Targeted Body Part Workouts | User | Select specific body parts for my workout | I can target those areas. | 2 | Should have
15 | Body Part Selection for Workouts | Quick Body Part Workout Search | User | Quickly find exercises by body part | I save time in selecting the right workout. | 2 | Should have
16 | Body Part Selection for Workouts | Personalized Workouts for Different Muscle Groups | User | Personalized workout suggestions for different muscle groups | I can balance my training. | 2 | Could have
17 | Body Part Selection for Workouts | Exclude Body Parts in Workouts for Injury Prevention | User | Exclude certain body parts from the workout | I don’t aggravate my injury. | 2 | Could have
18 | Workout Overview | Daily Workout Overview | Fitness user | See an overview of all planned workouts for the day | I know what exercises I need to complete. | 2 | Must have
19 | Workout Overview | Workout History and Progress Review | Fitness user | See a history of past workouts | I can analyze my progress. | 3 | Must have
20 | Workout Overview | Share Workout Overview with Coach or Friends | Fitness user | Share my workout overview with my coach or friends | I can get feedback or encouragement. | 3 | Could have
21 | Workout Overview | Overview of Completed and Upcoming Workouts | Fitness user | See both completed and upcoming workouts in one place | I can better organize my fitness routine. | 3 | Should have
22 | Comprehensive Workout & Health Management | Track Metrics | Fitness user | Track various health and fitness metrics (such as body weight, body fat %, sleep) | I can monitor my progress and make decisions based on those parameters. | 3 | Should have
23 | n/a
24 | Comprehensive Workout & Health Management | Track Water Intake | Fitness user | Log and monitor my daily water intake | I can stay hydrated and maintain healthy hydration habits | 4 | Could have
25 | n/a
26 | Comprehensive Workout & Health Management | Sync with Fitness Tracker Devices | Fitness user | Sync the app with my fitness tracker or smartwatch | I can automatically import my heart rate, steps, and other health data | 3 | Wont have
27 | Comprehensive Workout & Health Management | Adjust Workout Difficulty | Fitness user | Modify the intensity of my workout routine based on my fitness level | I can progress gradually without overexerting myself | 2 | Could have
28 | Simple UI Design | Tutorial | User | I want to be guided step by step on what to do | I can navigate through the app without frustrations |  | Could have
Story ID | Feauture Functionality | Story Title | As a | I want to | so that | Story Point | Priority

## First OLD User story (backup)
Story ID | Name | Feauture Functionality | Story Title | As a | I want to | so that | given… | when.. | then.. | Story Point | Priority
1 | Jason | Simple UI design | Simple and Intuitive | Fitness user | Use an app that is simple and intuitive | I can easily navigate through its features and log my workouts without any confusion or frustration. | I am using the app for the first time | I open the app and start exploring its features | the app should have a clean, user-friendly interface with clear instructions |  | Must have
2 | Jason | Creating Daily Workout | Creating workout routine | Fitness user | Track my progress | I can easliy track my exercises for today | the user has opened the app | the user selects an option to create workout | the app should remember the workout details |  | Must have
3 | Jason | Pick Body Part | Pick Body Part | Fitness user | Pick a body part | I can easily find the exercise I want for a particular body part | the user has initiated a workout routine for the day | the user presses "choose body part" | the app should display all exercises related to chosen body part |  | Could have
4 | Jason | Viewing Daily Workout | View workout routine | fitness user | View my workouts | I can get a brief overview of what i need to do today | that the user has created a workout routine for the day | the user has opened workout | the app should show all workouts for today |  | Must have
5 | Jason | Editing Daily Workout | Edit workout routine | fitness user | Edit my workouts | I can change change weight,reps and sets, RPE | the user has a created a workout routine for the day | the user has opened workout | the app should have editing capabilities in the workout window |  | Must have
6 | Jason | Cancelling Daily Workout | Cancel todays workout | fitness user | Cancel my workout | I can cancel the Daily Workout | the user has created a workout routine for the day | the user has opened workout | the app should have canceling capabilities in the workout window |  | Must have
7 | Jason | Timing Rest | Timer tracker | Fitness User | Have a timer | Im not spending too long resting | the user has created a workout routine for the day | the user has pressed the timer/clock symbol | the app should be able to create a timer |  | Could have
8 | Jason | Delete Exercise | Removing Exercise | Fitness User | Have the ability remove an exercise in my workout routine | I can remove that specific exercise | the user presses the icon next to workout name | the user presses remove exerise | the app should delete exercise |  | Could have
9 | Jason | Session Timer | Workout Routine Timer | Fitness User | Have a timer for my overall session | I can manage my time efficiently, ensuring I complete my workout within a specific timeframe | I have initialised my workout routine for the day | I set a timer for the duration of my workout | the app should start counting |  | Could have
10 | Jason | Save Workout | Save Workout Template | Fitnesss User | Have the choice to save my workout | I have the choice to Use the same template for another session | I have finished the workout | when the user presses save tempalte when asked | the app should save the exercise template in the template section |  | Must have
11 | Jason | Preview Exercise | Exercise Preview | Fitness User | to see a preview of specific exercises | I can remember how to perform them correctly and ensure proper form during my workout | I am selecting an exercise to include in my workout routineI tap on the exercise name or icon in the app | I tap on the exercise name or icon in the app | the app should display an image of the exercise, and a description of how to perform it |  | Won't have
12 | Ton | Template | Create workout template | User | Create a workout template | I can follow the excersises in the template. | The user wantsto create a workout template | The user accesses the "Create Template" feature | The user hsould be able to create a new workout template. |  | Must have
13 | Ton | Template | Share workout template | Personal Trainer | Share a workout template | I can share it to my trainees. | A personal trainer wants to share a workout template | The personal trainer has a custom template and uses the share feature | The template should be shared with other users of the app |  | Could have
14 | Ton | Excersises | Excersise Information | User | Read and understand what muscles the exercise targets | I can plan or try the excerise during the workout. | The user wants to understand which muscles an excercise targets | The user accesses the excercise information feature | They should be able to read and understand which muscles the exercise targets. |  | Could have
15 | Ton | Template | Use a template | Beginner weightlifter | Have access to a template | I know what to excercises to do during the workout. | A beginner weightlifter wants guidenace for their workout | They access an existing template | They should be able to see the exercises to perform during the workout |  | Must have
16 | Ton | Goals | Set Goals | Powerlifter | Set a goal for a personal record in an exercise | I know how close/far I am to the goal. | A powerlifter wants to track their progress toward a goal | They use the the "Set Goals" feature | They should be able to set a goal for a personal record in an exercise aand track their progress towards it |  | Could have
17 | Ton | Account Login | Login Account | Personal Trainer | Login to my trainees account | I can track their workout logs. | A personal trainer wants to track their trainees progress | They log in to a trainees' account | They should be able to view and track their trainees' workout logs |  | Must have
18 | Ton | Account Login | Account | User | Have an account | I have private worklogs I can access from multiple different devices. | A user wants to access their workout logs from different devices | They create and log in to their account | They should have private workout logs accessible from multiple devices. |  | Must have
19 | Ton | Logger | Reps in Reserve | Bodybuilder | Track my reps in reserve during a set | I can note down my intensity and see if I am optimising for hypertrophy. | A bodybuilder wants to track the intensity of their sets | They use the "Reps in Reserve" counter during their workout | They should be able to note down their reps in reserve and optimise for hypertrophy. |  | Could have
20 | Ton | Excercises | Create an excersise | User | Create an excercise | I can add it to the logger for future use. | The user wants to add a new exercise to their workout plan | The user accesses the "Create an exercise" feature | They should able to create a new exercise and add it to the list for future workouts. |  | Must have
21 | Ton | Excercises | Delete an excercise | User | Delete an excercise | I can delete an excercise If I believe I have no plans to do it due to injury concerns. | The user wants to remove an exercise they no longer plan to use | The user accesses the "Delete an exercise" feature | They should be able to remove the exercise from their list if they have no plans to do it. |  | Must have
22 | Ton | Excercises | Video Tutorial | User | See how to perform the excercise | I can do it with proper form. |  | They access the exercise and "Video Guide" feature | They should able to see a video guide that demonstrates the correct form of the exercise. |  | Wont have
23 | Ton | Health and Fitness Metrics | Track Metrics | User | Track various health and fitness metrics (such as body weight, body fat %, sleep) | I can monitor my progress and make decisions based on those parameters. | The user wants to monitor their fitness progress | The user accesses the "Track Metrics" feature | They should be able to input, view and update their health and fitness metrics such as height, weight, bmi, body fat percentage, blood pressure and sleep. |  | Could have